## Master Overview
📊 TakeOnTime / FOOD ORDERING APP — Full Project Task Tracker ¦ FlutterFlow · Supabase · FCM · Razorpay
All Sheets: UI/UX · Database · Backend · FlutterFlow · QA · Security ¦ 12-Week MVP Roadmap
# | Team / Role | Responsibilities | Sheet Name | Total Tasks | Not Started | In Progress | In Review | Done | Blocked | % Complete
1 | 🎨 UI/UX Designer | Figma screens, design system, prototypes, handoff | UI-UX Design | 16 | 16 | 0 | 0 | 0 | 0 | 0%
2 | 🗄️ DB Engineer | Supabase schema, RLS, functions, migrations, optimisation | Database | 16 | 16 | 0 | 0 | 0 | 0 | 0%
3 | ⚙️ Backend Engineer | Edge Functions, payments, notifications, settlement engine | Backend | 16 | 16 | 0 | 0 | 0 | 0 | 0%
4 | 🔧 FlutterFlow Dev | Customer/Vendor/Admin build, Supabase connect, screens, actions, deploy | FlutterFlow | 21 | 21 | 0 | 0 | 0 | 0 | 0%
| TOTAL |  |  | 69 | 69 | 0 | 0 | 0 | 0 | 0%
PHASES AT A GLANCE (1 phase = 1 week, per SRS Section 6)
Phase | Name | Timeline | What Happens
Phase 0 | Database & Project Setup | Week 1 | Backend-only: Supabase project, core schema, storage buckets, baseline RLS
Phase 1 | Authentication & Roles | Week 2 | Customer/Vendor/Admin login, RLS tested for all roles
Phase 2 | Vendor Onboarding & Organization | Week 3 | Register, documents, bank integration, branch setup, organization
Phase 3 | Menu Management | Week 4 | Categories, products, availability windows, store/inventory toggles
Phase 4 | Customer Discovery & Browsing | Week 5 | Vendor list, menu, product detail, geofenced marketplace
Phase 5 | Cart, Checkout & Payments + Self-Cancellation | Week 6 | Razorpay + COD checkout, invoice, 2-min self-cancel window
Phase 6 | Vendor Live Order Management | Week 7 | Order queue, accept/prep time, cancel + refund flows
Phase 7 | Customer Tracking & Notifications | Week 8 | Live tracker, ETA, OTP/QR pickup, FCM pushes
Phase 8 | Finance Engine | Week 9 | Settlement engine, COD reconciliation, cancellation refund logic
Phase 9 | Reports & Dashboards | Week 10 | Vendor earnings dashboard, exportable reports, order history
Phase 10 | Admin Panel | Week 11 | Platform dashboard, charts, top lists, audit log
Phase 11 | Testing, QA & Launch | Week 12 | Full regression, security review, Play Store & App Store submission

## UI-UX Design
🎨 UI/UX Designer — TakeOnTime App Task Tracker
Figma screens, design system, prototypes, handoff
# | Phase | Week | Task ID | Task Title | Description | Deliverable / Output | Priority | Status | Assigned To | Depends On | Est. Hours | Actual Hours | Notes
1 | Phase 0 | W1 | UX-001 | Design System & Style Guide | Define colour palette, typography, spacing grid, icon set, component tokens for Customer/Vendor/Admin apps | design-system Figma file | High | Not Started | UI/UX Designer | — | 16
2 | Phase 0 | W1 | UX-002 | App Navigation Wireframes | Wireframe core navigation for Customer app, Vendor dashboard, and Admin panel | Wireframe set | High | Not Started | UI/UX Designer | UX-001 | 10
3 | Phase 1 | W2 | UX-003 | Customer Onboarding Screens | Design Splash, OTP/Email login, Basic Profile, Organization Selector screens | Onboarding screen frames + prototype | Medium | Not Started | UI/UX Designer | UX-002 | 14
4 | Phase 1 | W2 | UX-004 | Vendor Onboarding Screens | Design Register, Business Profile, GST Status form, Document Upload screens | Vendor onboarding frames | Medium | Not Started | UI/UX Designer | UX-002 | 14
5 | Phase 2 | W3 | UX-005 | Vendor Branch & Bank Setup Screens | Design Branch Setup (hours, counter, holidays) and Bank Account Connect screens | Branch/bank screen frames | Medium | Not Started | UI/UX Designer | UX-004 | 8
6 | Phase 3 | W4 | UX-006 | Vendor Menu Management Screens | Design Category Manager, Product Editor, Availability Window Setting, Store & Inventory Toggles | Menu management frames | Medium | Not Started | UI/UX Designer | UX-004 | 16
7 | Phase 4 | W5 | UX-007 | Customer Discovery Screens | Design Vendor List (search/filter), Menu Screen (time-aware greying), Product Detail | Discovery screen frames | Medium | Not Started | UI/UX Designer | UX-003 | 14
8 | Phase 5 | W6 | UX-008 | Cart, Checkout & Payment Screens | Design Cart, Checkout (pickup-time picker), Payment Method Selector, Razorpay/COD confirmation screens | Checkout screen frames | Medium | Not Started | UI/UX Designer | UX-007 | 16
9 | Phase 5 | W6 | UX-009 | Cancel-Order Countdown Component | Design Cancel Order button with a live 2:00 countdown timer for the confirmation/tracking screen | Countdown component + states | Medium | Not Started | UI/UX Designer | UX-008 | 6
10 | Phase 5 | W6 | UX-010 | Invoice PDF Layout | Design the auto-generated customer invoice layout for both Razorpay (paid) and COD (pay-at-pickup) paths | Invoice template | Medium | Not Started | UI/UX Designer | UX-008 | 6
11 | Phase 6 | W7 | UX-011 | Vendor Kitchen Display Screens | Design Order Queue (sorted by pickup deadline), Accept Order Modal, Order Card, Cancel/Refund flow | Kitchen display frames | Medium | Not Started | UI/UX Designer | UX-006 | 14
12 | Phase 7 | W8 | UX-012 | Customer Tracking & Pickup Screens | Design Live Order Tracker, ETA Display, OTP/QR Pickup Screen | Tracking screen frames | Medium | Not Started | UI/UX Designer | UX-007 | 12
13 | Phase 8 | W9 | UX-013 | Vendor Settlement & Earnings Screens | Design "Cash Collected" action, Settlement Statement PDF (Razorpay vs COD shown separately) | Settlement screen frames | Medium | Not Started | UI/UX Designer | UX-011 | 10
14 | Phase 9 | W10 | UX-014 | Reports & Order History Screens | Design Vendor Earnings Dashboard, Reports Export, Customer Order History & Repeat Order | Reports/history frames | Medium | Not Started | UI/UX Designer | UX-013 | 10
15 | Phase 10 | W11 | UX-015 | Admin Panel Design | Design Admin Dashboard, Charts (orders/revenue/payment mix), Top Lists, Audit Log Viewer | Admin panel frames | Medium | Not Started | UI/UX Designer | UX-001 | 14
16 | Phase 11 | W12 | UX-016 | Store Assets & Screenshots | Design Play Store / App Store screenshots, feature graphic, app icon variants | Store graphics package | Medium | Not Started | UI/UX Designer | UX-015 | 8
TOTAL TASKS: 16 ¦ Est. Hours: | [10 empty] | 188

## Database
🗄️ DB Engineer — TakeOnTime App Task Tracker
Supabase schema, RLS, functions, migrations, optimisation
# | Phase | Week | Task ID | Task Title | Description | Deliverable / Output | Priority | Status | Assigned To | Depends On | Est. Hours | Actual Hours | Notes
1 | Phase 0 | W1 | DB-001 | Supabase Project Setup | Create Supabase project, configure Auth, Database, Storage, Edge Functions, Realtime, RLS | Supabase project live | Critical | Not Started |  | — | 4
2 | Phase 0 | W1 | DB-002 | Design Core Schema (20 tables) | Design and create the core schema per SRS Section 5, including payment_method / payment_status columns | Core schema live | Critical | Not Started |  | DB-001 | 10
3 | Phase 0 | W1 | DB-003 | Storage Buckets Setup | Create buckets: product-images, vendor-logos, organization-images, invoices, documents | Storage buckets live | Critical | Not Started |  | DB-001 | 3
4 | Phase 0 | W1 | DB-004 | Baseline RLS Policies | Write baseline RLS: Customer → own orders only; Vendor → own branch only; Admin → read everything | RLS policies live | Critical | Not Started |  | DB-002 | 8
5 | Phase 1 | W2 | DB-005 | users & vendors Tables | users (role, phone, email, auth fields); vendors (gst_registered, gstin); RLS tested for all 3 roles | Tables + RLS tested | Critical | Not Started |  | DB-002 | 6
6 | Phase 2 | W3 | DB-006 | Organization & Vendor Branch Tables | organizations, vendor_organizations, vendor_branches; vendors.documents_url, bank_account_ref | Tables live | Critical | Not Started |  | DB-002 | 8
7 | Phase 3 | W4 | DB-007 | Categories & Products Tables | categories; products (price, gst_percent, availability_start/end, stock_status) | Tables live | Critical | Not Started |  | DB-002 | 6
8 | Phase 4 | W5 | DB-008 | Geofenced Marketplace Query | Optimised query: vendors visible to a customer by selected organization, with public-browse fallback | Query tested | High | Not Started |  | DB-006 | 6
9 | Phase 5 | W6 | DB-009 | Orders, Payments & Invoice Tables | orders (pickup_time, payment_method); order_items; payments (gateway_ref/COD, status, amount); customer_invoices | Tables live | Critical | Not Started |  | DB-002 | 8
10 | Phase 5 | W6 | DB-010 | Self-Cancellation Fields | Add orders.customer_cancel_deadline (timestamptz), cancelled_by (enum), cancellable (boolean, default true) | Fields live + tested | Critical | Not Started |  | DB-009 | 4
11 | Phase 6 | W7 | DB-011 | Order Status & Notifications Tables | orders (status, prep_time_minutes, cancelled_reason, refund_type); notifications (order-event log) | Tables live | High | Not Started |  | DB-009 | 6
12 | Phase 7 | W8 | DB-012 | OTP/QR Pickup Fields | orders.otp_code / qr_token, collected_at; notifications FCM log | Fields live | High | Not Started |  | DB-009 | 4
13 | Phase 8 | W9 | DB-013 | Settlement Tables | payments status enum (incl. Collected, Refunded); vendor_settlements; vendor_settlement_items (nets Razorpay vs COD) | Tables live + tested | Critical | Not Started |  | DB-009 | 8
14 | Phase 9 | W10 | DB-014 | Reporting Aggregation Views | Aggregation views over orders, order_items, payments for vendor/customer dashboards | Views live | Medium | Not Started |  | DB-009 | 6
15 | Phase 10 | W11 | DB-015 | Audit Log & System Config Tables | audit_logs (payment/order/login trail); system_config (platform fee %, etc.) | Tables live | High | Not Started |  | DB-002 | 6
16 | Phase 11 | W12 | DB-016 | Production Migration & Backup | Numbered idempotent migration script for all tables/RLS/functions; configure production backups | migration_001.sql + backup verified | Critical | Not Started |  | DB-015 | 8
TOTAL TASKS: 16 ¦ Est. Hours: | [10 empty] | 101

## Backend
⚙️ Backend Engineer — TakeOnTime App Task Tracker
Edge Functions, payments, notifications, settlement engine
# | Phase | Week | Task ID | Task Title | Description | Deliverable / Output | Priority | Status | Assigned To | Depends On | Est. Hours | Actual Hours | Notes
1 | Phase 0 | W1 | BE-001 | Razorpay Account & API Keys | Create Razorpay account, generate API keys, store secrets in Supabase Vault | Keys in Vault | Critical | Not Started |  | — | 3
2 | Phase 1 | W2 | BE-002 | Edge Function: send_otp / verify_otp | Phone OTP or Email login for Customer, Vendor, Admin roles | Auth functions tested | Critical | Not Started |  | DB-005 | 8
3 | Phase 2 | W3 | BE-003 | Edge Function: vendor_document_notify | Notify admin/vendor on document upload; update verification status | Function tested | Critical | Not Started |  | DB-006 | 6
4 | Phase 5 | W6 | BE-004 | Edge Function: create_razorpay_order + Webhook | Launch Razorpay checkout, verify webhook signature, create order only on payment success | Function + webhook tested | Critical | Not Started |  | DB-009 | 12
5 | Phase 5 | W6 | BE-005 | Edge Function: process_cod_order | Create order immediately with payment_status = pending_cod; mark invoice "Pay at Pickup" | Function tested | Critical | Not Started |  | DB-009 | 6
6 | Phase 5 | W6 | BE-006 | Edge Function: generate_invoice | Auto-generate downloadable PDF invoice for both Razorpay and COD payment paths | Function tested | Critical | Not Started |  | BE-004 | 8
7 | Phase 5 | W6 | BE-007 | Edge Function: self_cancel_order | 2-minute self-service cancellation: Razorpay auto-refund via API or COD void, before vendor acceptance | Function tested | Critical | Not Started |  | DB-010 | 10
8 | Phase 6 | W7 | BE-008 | FCM Push: New Order Notification | Loud, repeating alert to vendor for incoming orders until accepted | Push tested | Critical | Not Started |  | DB-011 | 6
9 | Phase 6 | W7 | BE-009 | Edge Function: cancel_order (vendor-initiated) | Vendor cancellation with auto digital refund or manually logged cash refund | Function tested | Critical | Not Started |  | BE-007 | 6
10 | Phase 7 | W8 | BE-010 | FCM Push: Order Lifecycle Notifications | Accepted (with ETA), ready for pickup, reminder, cancelled — including COD cash-ready reminder | Push flows tested | Critical | Not Started |  | BE-008 | 6
11 | Phase 8 | W9 | BE-011 | Settlement Engine | Nets Razorpay payables against COD fees owed per vendor, daily or weekly; generates vendor statement PDF | Engine tested | Critical | Not Started |  | DB-013 | 14
12 | Phase 8 | W9 | BE-012 | Razorpay Refund API Integration | Automatic full refund for self-cancelled Razorpay orders; exclude both cancellation paths from settlement | Refund flow tested | Critical | Not Started |  | BE-007 | 6
13 | Phase 9 | W10 | BE-013 | Reports Export API | Daily/weekly/monthly vendor reports exportable as CSV/PDF | API tested | Critical | Not Started |  | DB-014 | 8
14 | Phase 10 | W11 | BE-014 | Admin Analytics Endpoints | Aggregation endpoints for dashboard: users, vendors, orders, revenue, fees, pending settlements | Endpoints tested | Critical | Not Started |  | DB-015 | 8
15 | Phase 11 | W12 | BE-015 | Load Testing — Orders & Payments | Simulate concurrent order/payment traffic; identify and fix bottlenecks | Load test report | Critical | Not Started |  | BE-011 | 8
16 | Phase 11 | W12 | BE-016 | Webhook Signature Hardening | Final security pass on Razorpay webhook signature verification before launch | Hardening verified | Critical | Not Started |  | BE-004 | 4
TOTAL TASKS: 16 ¦ Est. Hours: | [10 empty] | 119

## FlutterFlow
🔧 FlutterFlow Dev — TakeOnTime App Task Tracker
Customer/Vendor/Admin build, Supabase connect, screens, actions, deploy
# | Phase | Week | Task ID | Task Title | Description | Deliverable / Output | Priority | Status | Assigned To | Depends On | Est. Hours | Actual Hours | Notes
1 | Phase 0 | W1 | FF-001 | FlutterFlow Project Setup | Create Customer, Vendor, Admin projects/apps; configure theme from design system | Projects live | Critical | Not Started |  | UX-001 | 6
2 | Phase 0 | W1 | FF-002 | Connect Supabase & Import Schema | Connect Supabase URL + anon key, import all core tables | Supabase connected | Critical | Not Started |  | DB-002 | 3
3 | Phase 1 | W2 | FF-003 | Login/Signup — All Roles | Customer Login/Signup (OTP/Email), Vendor Login/Signup, Admin Login + Profile forms | Auth screens live | Critical | Not Started |  | BE-002 | 10
4 | Phase 2 | W3 | FF-004 | Vendor Onboarding Flow | Register → Business Profile → Document Upload → Bank Connect → Branch Setup → Select/Create Org | Vendor onboarding live | Critical | Not Started |  | UX-004 | 16
5 | Phase 3 | W4 | FF-005 | Vendor Menu Management | Category Manager, Product Editor, Availability Window Setting, Store & Inventory Toggles | Menu management live | Critical | Not Started |  | UX-006 | 16
6 | Phase 4 | W5 | FF-006 | Customer Discovery Screens | Vendor List (search/nearby/category), Menu Screen (time-aware), Product Detail | Discovery live | Critical | Not Started |  | UX-007 | 14
7 | Phase 5 | W6 | FF-007 | Cart & Checkout | Cart, Checkout (pickup-time picker), Payment Method Selector | Checkout live | Critical | Not Started |  | UX-008 | 12
8 | Phase 5 | W6 | FF-008 | Razorpay Checkout Integration | UPI/Card/Netbanking checkout wired to BE-004; Order Created + Invoice Generated on success | Integration tested | Critical | Not Started |  | BE-004 | 10
9 | Phase 5 | W6 | FF-009 | COD Confirmation & Invoice Screen | COD confirmation screen; auto-generated downloadable PDF invoice for both payment paths | Screens live | Critical | Not Started |  | BE-005 | 6
10 | Phase 5 | W6 | FF-010 | Self-Cancel Button + Countdown | Cancel Order button with live 2:00 countdown on Confirmation/Tracking screen; disables on deadline/acceptance | Component live + tested | Critical | Not Started |  | UX-009 | 8
11 | Phase 6 | W7 | FF-011 | Vendor Kitchen Display | Order Queue sorted by pickup deadline, Accept Order Modal (5/10/15/30 min), Order Card with COD flag | Kitchen display live | Critical | Not Started |  | UX-011 | 14
12 | Phase 6 | W7 | FF-012 | Vendor Cancel/Refund Flow | Cancel + Auto-Refund and Cancel + Cash Refund actions on the order card | Flow tested | High | Not Started |  | FF-011 | 6
13 | Phase 7 | W8 | FF-013 | Customer Live Order Tracker | Tracker (Received→Accepted→Preparing→Ready→Collected), dynamic ETA display | Tracker live | Critical | Not Started |  | UX-012 | 10
14 | Phase 7 | W8 | FF-014 | OTP/QR Pickup Verification | Customer OTP/QR pickup screen; Vendor scan-to-verify screen | Screens tested | Critical | Not Started |  | FF-013 | 8
15 | Phase 8 | W9 | FF-015 | Cash Collected & Settlement Statement | Vendor "Cash Collected" action button; Settlement Statement PDF viewer (Razorpay vs COD) | Screens live | High | Not Started |  | UX-013 | 8
16 | Phase 9 | W10 | FF-016 | Vendor Earnings Dashboard & Export | Today/7-day/month/year/lifetime earnings view; CSV/PDF report export | Dashboard live | Medium | Not Started |  | UX-014 | 10
17 | Phase 9 | W10 | FF-017 | Customer Order History & Repeat Order | Order history list, invoice re-download, repeat-order action | Screens live | Medium | Not Started |  | FF-006 | 6
18 | Phase 10 | W11 | FF-018 | Admin Dashboard & Charts | Users/vendors/orders/revenue/fees/settlements dashboard; order & revenue charts; top lists | Admin dashboard live | High | Not Started |  | UX-015 | 14
19 | Phase 10 | W11 | FF-019 | Admin Audit Log Viewer | Payments/orders/logins audit trail viewer | Viewer live | Medium | Not Started |  | DB-015 | 6
20 | Phase 11 | W12 | FF-020 | Android & iOS Build + Regression | Build both platforms; full regression pass across every screen built in Weeks 1–11 | Builds tested | Critical | Not Started |  | FF-019 | 12
21 | Phase 11 | W12 | FF-021 | Play Store & App Store Submission | Submit production builds with store listings, screenshots, privacy policy | Apps submitted | Critical | Not Started |  | FF-020 | 6
TOTAL TASKS: 21 ¦ Est. Hours: | [10 empty] | 201

## QA & Testing
🧪 QA Engineer — TakeOnTime App Task Tracker
Test plans, functional, regression, payment edge cases
# | Phase | Week | Task ID | Task Title | Description | Deliverable / Output | Priority | Status | Assigned To | Depends On | Est. Hours | Actual Hours | Notes
1 | Phase 0 | W1 | QA-001 |  |  |  | Critical | Not Started |  | — | 4
2 | Phase 1 | W2 | QA-002 |  |  |  | Critical | Not Started |  | FF-003 | 6
3 | Phase 2 | W3 | QA-003 |  |  |  | High | Not Started |  | FF-004 | 6
4 | Phase 3 | W4 | QA-004 |  |  |  | High | Not Started |  | FF-005 | 4
5 | Phase 4 | W5 | QA-005 |  |  |  | High | Not Started |  | FF-006 | 4
6 | Phase 5 | W6 | QA-006 |  |  |  | Critical | Not Started |  | FF-008 | 8
7 | Phase 5 | W6 | QA-007 |  |  |  | Critical | Not Started |  | FF-010 | 6
8 | Phase 6 | W7 | QA-008 |  |  |  | High | Not Started |  | FF-011 | 6
9 | Phase 7 | W8 | QA-009 |  |  |  | High | Not Started |  | FF-014 | 6
10 | Phase 8 | W9 | QA-010 |  |  |  | Critical | Not Started |  | BE-011 | 8
11 | Phase 9 | W10 | QA-011 |  |  |  | Medium | Not Started |  | FF-016 | 6
12 | Phase 10 | W11 | QA-012 |  |  |  | Medium | Not Started |  | FF-018 | 6
13 | Phase 11 | W12 | QA-013 |  |  |  | Critical | Not Started |  | QA-012 | 12
14 | Phase 11 | W12 | QA-014 |  |  |  | Critical | Not Started |  | QA-006 | 6
15 | Phase 11 | W12 | QA-015 |  |  |  | Critical | Not Started |  | QA-013 | 4
TOTAL TASKS: 15 ¦ Est. Hours: | [10 empty] | 92

## Edge Functions
⚙️ Edge Functions Catalog — TakeOnTime App
Backend service layer — one Edge Function per business operation
# | Edge Function | Service Module | Trigger | Purpose | Week Built
1 | send_otp / verify_otp | Authentication Service | Client call | Issue and verify phone/email OTP for all three roles | W2
2 | create_order | Order Service | Client call (post payment success / COD select) | Validates cart, consumes stock hold, creates order and order_items, deducts inventory., sets cancellable window | W6
3 | verify_payment | Payment Service | Razorpay webhook | Verifies webhook, matches razorpay_order_id, updates payment, calls create_order. | W6
4 | create_invoice / generate_pdf | Invoice Service | After create_order | Renders and stores the customer invoice PDF (Razorpay-paid or Pay-at-Pickup) | W6
5 | cancel_order (self-cancel) | Order Service | Client call (customer, within 2-min window) | Razorpay auto-refund via API or COD void, before vendor acceptance | W6
6 | create_payment_order | Payment Service | Client Call | Creates Razorpay Order, creates stock hold, writes preliminary payment | W7
7 | vendor_accept_order | Order Service | Client call (vendor) | Accepts order, sets prep_time_minutes, notifies customer | W7
8 | cancel_order (vendor-initiated) | Order Service | Client call (vendor) | Vendor cancellation with auto digital refund or manually logged cash refund | W7
9 | vendor_document_notify | Vendor Service | On document upload | Notifies admin/vendor, updates verification status | W3
10 | settlement_run | Settlement Service | Cron (daily/weekly) | Nets Razorpay payables vs COD fees owed per vendor, writes vendor_settlements | W9
11 | send_notifications | Notification Service | Called by other functions | Central FCM fan-out + notifications log writer | W7–W8

## Cron Jobs
⏰ Cron Jobs / Scheduled Tasks — TakeOnTime App
Scheduled backend execution required beyond request/response Edge Functions
# | Cron Job | Schedule | What It Does | Week Built
1 | cron_scheduled_orders | Every minute | Auto-sends “Order for Later” orders to the vendor at the correct lead time before pickup | W7
2 | cleanup_expired_cancellations | Every minute | Flips orders.cancellable to false once customer_cancel_deadline passes | W7
3 | release_expired_stock_holds | Every minute | Releases expired stock reservations | W8
4 | settlement_run | Daily or weekly (configurable) | Runs the settlement engine and generates vendor statements | W9
5 | notification_reminders | Every few minutes | COD pickup reminders, “order ready” nudges not yet acknowledged | W8
6 | invoice_cleanup | Daily | Removes/archives expired or orphaned invoice files from storage | W12
7 | analytics_refresh | Hourly | Refreshes materialized views backing the vendor and admin dashboards | W10

## Feature Tracker
🧵 Feature Tracker (Cross-Layer View) — TakeOnTime App
Every feature traced across Flow, UI, Database, Backend, Edge Function, API, and Testing ]
# | Feature | Flow | UI | Database | Backend | Edge Function | API | Testing
1 | Authentication (OTP/Email, 3 roles) | Login → Verify → Profile | Login/Signup screens (Customer/Vendor/Admin) | users, device_tokens | Authentication Service | send_otp / verify_otp | — | QA-002
2 | Vendor Onboarding | Register → Docs → Bank → Branch → Org | Vendor onboarding screens | vendors, vendor_branches, vendor_organizations | Vendor Service | vendor_document_notify | — | QA-003
3 | Menu Management | Category → Product → Images → Availability | Category Manager, Product Editor | categories, products, product_images | Vendor Service | — | — | QA-004
4 | Customer Discovery | Org select → Vendor List → Menu → Product | Vendor List, Menu, Product Detail | organizations, vendor_organizations, products (read) | — | — | Geofenced query | QA-005
5 | Cart & Checkout (Razorpay) | Cart → Checkout → Pay → Order → Invoice | Cart, Checkout, Razorpay Checkout, Invoice | orders, order_items, payments, customer_invoices | Order + Payment + Invoice Services | create_payment_order verify_payment create_order create_invoice | Razorpay Orders/Webhook API | QA-006
6 | Cart & Checkout (COD) | Cart → Checkout → Order → Invoice (Pay at Pickup) | COD Confirmation Screen, Invoice | orders, order_items, payments, customer_invoices | Order + Invoice Services | create_order, create_invoice | — | QA-006
7 | Self-Cancellation (2-min window) | Cancel tap → Refund/Void → order_events | Cancel button + countdown | orders (cancel fields), order_events | Order Service | cancel_order | Razorpay Refund API | QA-007
8 | Scheduled Orders (“Order for Later”) | Save → cron → Auto-send to vendor | Pickup-time picker (Later option) | orders (pickup_time) | Order Service | create_order | — | QA-006 / QA-008
9 | Vendor Live Order Management | Notify → Accept → Prep → Ready → Collected | Kitchen Display, Accept Modal, Order Card | orders, order_events, notifications | Order + Notification Services | vendor_accept_order, cancel_order, send_notifications | — | QA-008
10 | Customer Tracking & Pickup | Realtime tracker → ETA → OTP/QR → Collected | Live Tracker, ETA, OTP/QR Screen | orders (otp/qr, collected_at), order_events | Notification Service | send_notifications | Realtime (orders) | QA-009
11 | Settlement Engine | Cron → Net payables/receivables → Statement | Settlement Statement PDF, Cash Collected button | payments, vendor_settlements, vendor_settlement_items | Settlement Service | settlement_run | Razorpay Payouts (future) | QA-010
12 | Reports & Dashboards | Aggregate → Filter → Export | Earnings Dashboard, Reports Export, Order History | Aggregation views over orders/payments | Invoice Service | generate_pdf | Reports Export API | QA-011
13 | Admin Panel | Aggregate platform-wide → Charts → Audit | Admin Dashboard, Charts, Top Lists, Audit Log | audit_logs, system_config | — | — | Admin Analytics Endpoints | QA-012
14 | Notifications (FCM, multi-device) | Trigger → Fan-out → Push → Log | Notification Center (Vendor) | notifications, device_tokens | Notification Service | send_notifications | FCM API | QA-008 / QA-009

## updates
🗄️ New & Planned Tables — TakeOnTime App
Additions beyond the original 13 core table groups
# | Table | Status | Purpose / Replaces
1 | product_images | MVP (Week 1/4) | Replaces products.image_url — one product can carry a gallery of images
2 | order_events | MVP (Week 1/6–8) | Replaces relying on orders.status alone — stores full status history (Accepted/Preparing/Ready/Collected/Cancelled) for analytics, audits, support
3 | device_tokens | MVP (Week 1/2) | Replaces a single FCM token on users — one user can have many devices
4 | favorite_vendors | Post-MVP | Customer's saved vendors for quick access
5 | favorite_products | Post-MVP | Customer's saved products — speeds up repeat ordering
6 | customer_addresses | Post-MVP | Saved addresses; unused for pickup-only MVP but positions the app for future delivery
7 | support_tickets | Post-MVP | Customer support requests, optionally linked to an order
8 | vendor_holidays | Post-MVP | Holiday calendar as its own table instead of a field inside vendor_branches
| stock_holds |  | Temporary inventory reservation between stock validation and payment